## Sprint Roadmap
Action Bridge — Sprint Planning & Roadmap
Last updated: June 2026 ¦ Backend: FastAPI + SQLite/PostgreSQL ¦ Frontend: React + Vite + Tailwind
ID | Feature / Task | Status | Priority | Sprint | Effort | Dependencies | Notes
S1.1 | Backend CRUD: Projects, Document Types (JSON Schema) | Done | High | Sprint 1 | 5d
S1.2 | Database setup + Alembic migrations | Done | High | Sprint 1 | 2d
S1.3 | Docker Compose (PostgreSQL + app) | Done | Medium | Sprint 1 | 1d
S1.4 | Frontend: Project + Document Type CRUD pages | Done | High | Sprint 1 | 4d
S2.1 | Document lifecycle FSM (received→pending_review→approved/rejected) | Done | High | Sprint 2 | 3d
S2.2 | Document submission with schema validation | Done | High | Sprint 2 | 2d
S2.3 | Document inbox with filters + audit timeline | Done | High | Sprint 2 | 3d
S2.4 | Schema-driven form in DocumentDetail + type coercion | Done | High | Sprint 2 | 4d
S2.5 | Dark mode + glass-morphism design system | Done | Medium | Sprint 2 | 2d
S3.1 | JWT auth: User + ApiKey models | Done | High | Sprint 3 | 3d
S3.2 | Permission-based RBAC (admin/reviewer/viewer) | Done | High | Sprint 3 | 2d
S3.3 | Login/Register/Setup/Status endpoints + API key auth | Done | High | Sprint 3 | 2d
S3.4 | Frontend: Login, Setup wizard, AuthContext | Done | High | Sprint 3 | 3d
S3.5 | Setup wizard (replaced seed_admin, .setup-complete marker) | Done | Medium | Sprint 3 | 1d
S4.1 | Visual Schema Builder (add/remove/reorder fields, table support) | Done | High | Sprint 4 | 4d
S4.2 | Advanced JSON Editor (undo/redo stacks, Ctrl+Z/Y) | Done | Medium | Sprint 4 | 2d
S4.3 | Schema converters (flat fields ↔ table round-trip) | Done | Medium | Sprint 4 | 1d
S4.4 | User Management (list/role/is_active toggle) | Done | High | Sprint 4 | 2d
S4.5 | API Key management + Dashboard/Stats with charts | Done | High | Sprint 4 | 3d
S4.6 | Bulk delete (projects, doc-types, documents) | Done | Medium | Sprint 4 | 2d
S4.7 | Settings: Reset System with type-to-confirm | Done | Medium | Sprint 4 | 1d
S4.8 | Rename app to 'Action Bridge' | Done | Low | Sprint 4 | 0.5d
S4b.1 | Field-level validation rules (confidence_min, length, regex, range) | Done | High | Sprint 4b | 4d | S4.1
S4b.2 | AND/OR pattern groups with negate flag | Done | High | Sprint 4b | 2d
S4b.3 | Built-in patterns (istext, isnumber, isemailid, isip, etc.) | Done | Medium | Sprint 4b | 1d
S4b.4 | RegexPattern model + CRUD at /api/v1/regex-patterns | Done | Medium | Sprint 4b | 2d
S4b.5 | ValidationRulesDialog: 3-source picker (builtin/saved/custom) | Done | High | Sprint 4b | 3d
S4b.6 | RegexBuilder component with live match highlighting | Done | Medium | Sprint 4b | 2d
S4b.7 | ValidationPatternsPage at /validation-patterns | Done | Medium | Sprint 4b | 2d
S4b.8 | Migration 004: regex_patterns table | Done | High | Sprint 4b | 0.5d
S4b.9 | confidence_min mandatory (default 95%, non-removable) | Done | High | Sprint 4b | 0.5d
S4b.10 | Auto-approve when all validations pass | Done | High | Sprint 4b | 0.5d
S4c.1 | Email service: SMTP send with HTML/plain templates | Done | High | Sprint 4c | 3d
S4c.2 | Models: ProjectMembership, Notification, DocTypeSubscription, Comment, Attachment | Done | High | Sprint 4c | 2d
S4c.3 | Project model: created_by + visibility columns | Done | High | Sprint 4c | 0.5d
S4c.4 | Settings router: Company/SMTP/Password Policy CRUD + logo upload | Done | High | Sprint 4c | 2d
S4c.5 | Notifications router (list/unread/mark-read/mark-all-read) | Done | Medium | Sprint 4c | 1d
S4c.6 | Comments router (threaded create/edit/delete) | Done | Medium | Sprint 4c | 1.5d
S4c.7 | Attachments router (upload/list/delete with mime+size filter) | Done | Medium | Sprint 4c | 1.5d
S4c.8 | Invitations router (list-pending/accept/decline) | Done | Medium | Sprint 4c | 1d
S4c.9 | Subscriptions router (list/upsert/delete) | Done | Low | Sprint 4c | 0.5d
S4c.10 | Auth: user create/delete, password change, password reset flow | Done | High | Sprint 4c | 2d
S4c.11 | Project service: memberships (invite/accept/remove/role) | Done | High | Sprint 4c | 2d
S4c.12 | Backend main: register all routers + static uploads mount | Done | High | Sprint 4c | 0.5d
S4c.13 | Migration 005: all new tables + projects FKs (SQLite batch mode) | Done | High | Sprint 4c | 1d
S4d.1 | SettingsPage: tabbed UI (Company/SMTP/Password/Danger) | Done | High | Sprint 4d | 2d | S4c.4
S4d.2 | TopBar: notification bell dropdown with mark-read + password change modal | Done | High | Sprint 4d | 2d | S4c.5
S4d.3 | DocumentDetail: threaded comments section + attachments upload | Done | High | Sprint 4d | 3d | S4c.6+S4c.7
S4d.4 | UserManagement: create user form + delete button (self-protected) | Done | High | Sprint 4d | 1.5d | S4c.10
S4d.5 | MembersPage: invite/remove/change-role with user selector | Done | High | Sprint 4d | 2d | S4c.11
S4d.6 | ProjectDetail: Members tab added | Done | Medium | Sprint 4d | 0.5d
S4d.7 | DocumentTypeList: bell toggle subscription per card | Done | Medium | Sprint 4d | 1d | S4c.9
S4d.8 | ForgotPasswordPage + ResetPasswordPage (2-step flow) | Done | Medium | Sprint 4d | 1.5d | S4c.10
S4d.9 | Settings SMTP: Send Test Email button | Done | Low | Sprint 4d | 0.5d
S5.1 | Dashboard charts: daily volume line chart (last 7 days) | In Progress | High | Sprint 5 | 2d | S4d.6 | Use recharts; fetch stats from /projects/{id}/stats
S5.2 | Dashboard charts: status distribution pie/bar chart | In Progress | High | Sprint 5 | 1.5d
S5.3 | Dashboard: recent activity feed (last 5 audit events) | In Progress | Medium | Sprint 5 | 1.5d
S5.4 | Invitations pending badge in sidebar | Pending | Medium | Sprint 5 | 1d | S4c.8 | Fetch GET /api/v1/invitations count
S5.5 | Loading/empty/error states for comments, attachments, members | Pending | Medium | Sprint 5 | 2d |  | Refine existing components
S5.6 | Error boundaries for all pages | Pending | Low | Sprint 5 | 1d |  | React error boundary pattern
S5.7 | Document detail: download attachment link (a href to /uploads/...) | Pending | Low | Sprint 5 | 0.5d | S4c.7 | Make attachment filename clickable
S6.1 | Backend: pytest setup + conftest (test DB, auth fixtures) | Pending | High | Sprint 6 | 2d
S6.2 | Backend: test auth endpoints (login, register, setup, me, users) | Pending | High | Sprint 6 | 2d
S6.3 | Backend: test project CRUD + member invite/accept/remove | Pending | High | Sprint 6 | 2d
S6.4 | Backend: test document submission, validation rules, FSM transitions | Pending | High | Sprint 6 | 3d
S6.5 | Backend: test comments, attachments, notifications, subscriptions | Pending | Medium | Sprint 6 | 2d
S6.6 | Backend: test regex-patterns CRUD + pattern resolution in validation | Pending | Medium | Sprint 6 | 1.5d
S6.7 | Frontend: vitest + testing-library setup | Pending | Medium | Sprint 6 | 1d
S6.8 | Frontend: test schema builder, validation rules dialog, regex builder | Pending | Medium | Sprint 6 | 3d
S6.9 | Frontend: test auth flow (login, setup, password reset) | Pending | Medium | Sprint 6 | 2d
S7.1 | Docker Compose for production (backend + frontend + nginx) | Pending | High | Sprint 7 | 2d
S7.2 | GitHub Actions CI: lint + typecheck + test on PR | Pending | High | Sprint 7 | 1.5d | Sprint 6
S7.3 | GitHub Actions CD: deploy on merge to main | Pending | Medium | Sprint 7 | 1.5d
S7.4 | Environment variable documentation (.env.example full) | Pending | Low | Sprint 7 | 0.5d
S7.5 | PostgreSQL migration production check | Pending | High | Sprint 7 | 1d |  | Test Alembic migrations against fresh PostgreSQL
B.1 | Webhook support: notify external systems on document events | Backlog | Low | Future | 3d |  | POST to configured webhook URL on status change
B.2 | Export documents to CSV/Excel | Backlog | Low | Future | 2d
B.3 | Multi-page document support (batch submission) | Backlog | Low | Future | 4d |  | Submit multiple documents at once
B.4 | Activity log page (global audit events, not per-document) | Backlog | Low | Future | 2d
B.5 | Dark mode persistence (localStorage/user preference) | Backlog | Low | Future | 0.5d
B.6 | Internationalization (i18n) support | Backlog | Low | Future | 5d

## Sprint 5 — Dashboard & Polish
Sprint 5: Dashboard & Polish
Goal: Complete the project dashboard with charts, polish new features, handle edge cases
Step | Task | Status | Effort | Files to modify | Acceptance Criteria | Notes
1 | Install recharts package | Pending | 0.1d | frontend/package.json | npm install recharts
2 | Dashboard: daily volume line chart | Pending | 2d | frontend/src/pages/ProjectDashboard.tsx | Line chart shows 7-day document volume from /projects/{id}/stats.daily_volume; dates on X, count on Y; different colored lines per status | Use ResponsiveContainer, XAxis/YAxis, Tooltip, Legend, CartesianGrid, Line
3 | Dashboard: status distribution pie chart | Pending | 1.5d | frontend/src/pages/ProjectDashboard.tsx | Pie chart shows breakdown from stats.status_breakdown; labels with count + %, tooltip, color map per status (emerald=approved, amber=pending, red=rejected, gray=received) | Use PieChart, Pie, Cell, Tooltip
4 | Dashboard: recent activity feed | Pending | 1.5d | frontend/src/pages/ProjectDashboard.tsx | Shows latest 5 audit events across all documents in project; displays action, document type, timestamp, actor; clickable to navigate to document detail | Add new endpoint or reuse existing audit data; show skeleton while loading
5 | Invitations pending badge in sidebar | Pending | 1d | frontend/src/components/layout/Sidebar.tsx, frontend/src/contexts/AuthContext.tsx | Sidebar shows small red badge with pending invitation count next to bell or user section; auto-fetches every 30s | Fetch GET /api/v1/invitations, count items with status=pending
6 | Loading/empty/error states polish | Pending | 2d | Various: DocumentDetail, MembersPage, DocumentTypeList, TopBar | All new components show Skeleton while loading, empty state message when no data, error banner when API fails | Already partially done; audit and fix any missing states
7 | Attachment download link | Pending | 0.5d | frontend/src/pages/documents/DocumentDetail.tsx | Attachment file name is a clickable link that opens /uploads/{file_path} in new tab | Right now it's just a display; make it a functional <a> tag
8 | Error boundary component | Pending | 1d | frontend/src/components/shared/ErrorBoundary.tsx | Wrap each route page in ErrorBoundary; shows friendly error UI with retry button | Standard React error boundary + fallback UI
9 | Final verification: tsc + build + backend start | Pending | 0.5d |  | All TypeScript compiles, frontend builds, backend starts without errors

## Sprint 6 — Testing
Sprint 6: Testing
Goal: Add comprehensive test coverage for backend API endpoints and frontend components
Step | Task | Status | Effort | Files to modify | Acceptance Criteria | Notes
1 | Backend: pytest + httpx + test DB setup | Pending | 2d | backend/conftest.py, backend/tests/conftest.py | async test client with SQLite test DB, fixture for admin user, fixture for auth headers | Use pytest-asyncio, httpx.AsyncClient, separate test DB file
2 | Backend: test auth endpoints | Pending | 2d | backend/tests/test_auth.py | Tests for: setup, register, login, me, users CRUD, password change, password reset, API key CRUD
3 | Backend: test project + membership | Pending | 2d | backend/tests/test_projects.py | Tests for: create/read/update/delete project, list with visibility filter, invite/accept/decline/remove/role-change
4 | Backend: test document + validation | Pending | 3d | backend/tests/test_documents.py | Tests for: submit document, schema validation, validation rules (confidence, patterns, AND/OR groups), FSM transitions, audit events, bulk ops
5 | Backend: test new routers (comments, attachments, notifications, subscriptions) | Pending | 2d | backend/tests/test_social.py | Tests for: threaded comments CRUD, attachment upload/list/delete, notification mark-read, subscription upsert/delete
6 | Frontend: vitest + testing-library setup | Pending | 1d | frontend/vitest.config.ts, frontend/src/test-setup.ts | vitest configured with jsdom, testing-library render helpers, mock for API calls
7 | Frontend: test SchemaBuilder + ValidationRulesDialog | Pending | 3d | frontend/src/tests/ | Tests for: field add/remove/reorder, type change, table column editor, validation rules picker, confidence slider | Use MSW or manual fetch mocks
8 | Frontend: test auth flow | Pending | 2d | frontend/src/tests/ | Tests for: login, setup wizard, forgot/reset password, auth context behavior

## Sprint 7 — Deployment and CI-CD
Sprint 7: Deployment & CI/CD
Goal: Production-ready deployment with CI/CD pipeline
Step | Task | Status | Effort | Files to modify | Acceptance Criteria | Notes
1 | Production Docker Compose | Pending | 2d | docker-compose.prod.yml, frontend/Dockerfile, backend/Dockerfile, nginx/ | Multi-service compose: backend (gunicorn + uvicorn workers), frontend (nginx serving static build), postgres; env vars via .env.prod | Use multi-stage build for frontend
2 | GitHub Actions CI pipeline | Pending | 1.5d | .github/workflows/ci.yml | On PR: run backend tests (pytest), run frontend typecheck + build, lint (ruff for Python, ESLint for TS)
3 | GitHub Actions CD pipeline | Pending | 1.5d | .github/workflows/cd.yml | On merge to main: build + push Docker images to registry, deploy to VPS (SSH + docker-compose pull/up)
4 | Env docs + .env.example cleanup | Pending | 0.5d | backend/.env.example | Full documentation of all env vars: SECRET_KEY, DATABASE_URL, SMTP_*, UPLOAD_DIR
5 | PostgreSQL migration verification | Pending | 1d | backend/alembic/ | Run all migrations against fresh PostgreSQL DB; fix any dialect-specific SQL issues (JSON, timestamps, etc.) | SQLite has some leniencies that Postgres does not

## Backlog & Future
Backlog & Future Features
ID | Feature | Effort | Priority | Dependencies | Notes
B.1 | Webhook support: notify external systems on document events | 3d | Low | Email service | POST to configured webhook URL on status change
B.2 | Export documents to CSV/Excel | 2d | Low |  | Download all documents in a project as a spreadsheet
B.3 | Multi-page document batch submission | 4d | Low |  | Submit multiple documents in one API call / form
B.4 | Global activity log page | 2d | Low |  | View all audit events across all projects
B.5 | Dark mode persistence (localStorage) | 0.5d | Low |  | Remember dark mode preference across sessions
B.6 | i18n / localization support | 5d | Low |  | React-Intl or react-i18next setup with English as base
B.7 | Document template cloning (copy doc type to another project) | 1.5d | Low | Sprint 4b | Clone entire schema + validation rules
B.8 | Comment @mentions + in-app notification | 2d | Low | Comments + Notifications | @username triggers notification to that user